## Project Template
Project Charter
Project Description
Text Here
Business Need
Text Here
Project Ownership / Approval
Project Manager | Russell Walton |  | Project Champion | Paul Smith |  | Approval Date | 2017-05-17
Project Number | PT-101
Financial & Project Timing Goals
Payback |  |  | Capital/Expense |  |  | Milestones (Schedule)
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Incremental Sales | $350M |  | Expenses Incemental to Operating Budget | $.45M |  | Complete End-User Studies | 2015-09-01
Profitability (% OI) | 20% |  |  |  |  | Complete Prototype Field Testing | 2016-05-01
Payback Period (yrs) | 1.5 |  | Capital | $8.5M |  | Manufacturing Pilot Lot | 2017-05-01
Annual Savings | N/A |  | Other |  |  | Launch | 2017-08-01
Resources & Project Risks
Internal Resouces |  |  | External Services |  |  | Project Risks
| Total Hours | Peak Hrs/Wk |  | Budget | Actual |  | Medium | High
Far East Sourcing Team | 2000 | 80 | Supplier Design Services | $3.2M |  | IP Restrictions |  | X
R&D Team | 2500 | 120 | Market Research | $0.6M |  | Call Center Capacity | X
Field Test Team | 280 | 40 | Consulting - Call Center Expansion | $0.45M
Marketing / Market Research | 640 | 80